INTERNATIONAL WATERS PROJECT IMPLEMENTING THE

STRATEGIC ACTION PROGRAMME FOR THE INTERNATIONAL

WATERS OF THE PACIFIC SMALL ISLAND DEVELOPING

STATES

Designing monitoring plans in the Pacific Islands International Waters Project

Meetings of the Pacific National Biodiversity Strategic Action Plan Coordinators (NBSAP) and Pacific Islands Roundtable for Nature Conservation Management Group – Papua New Guinea, July 20 – 29, 2005

Holland, P., Mahanty, S, Stacey, N., Nimoho, L., Wright, D. and Menzies, S.*

Foreword

During 2004 to 2005, the IWP supported 13 countries in developing monitoring plans to support in-country activities they were implementing to improve resource management. This paper documents the rationale behind this decision and the process subsequently adopted in the IWP to develop monitoring plans. The paper also outlines the nature of monitoring plans developed, the kinds of indicators identified and adopted to support resource management and the lessons learned in the process. Readers are referred to detailed meeting documents for further information.

# Acronyms

GEF	Global Environment Facility

ICWM	integrated coastal and watershed management

IWP	International Waters Project

NC	national coordinator

PCU	project coordination unit

SAP	strategic action programme

SPREP	Secretariat of the Pacific Regional Environment Programme

UNDP	United Nations Development Project

VFMCs	village fisheries management committees

* Paula Holland, Drew Wright, Steve Menzies and Natasha Stacey work at the Project Coordination Unit of the International Waters Project, SPREP, Apia, Samoa.

* Leah Nimoho is the National Coordinator with IWP Vanuatu, operating through the Department of Environment.

* Sango Mahanty works in Resource Management in the Asia-Pacific Program, Australian National University, Canberra, Australia.

Table of contents

Acronyms	ii

1	Introduction	2

2	Monitoring under the IWP	2

3	Starting off the monitoring plan process	2

3.1	Review of relevant work/information	2

3.2	Dedicated planning workshops for the IWP	2

4	Identifying project goals and objectives	2

4.1	Lessons learned related to goals and objectives	2

5	Identification of indicators	2

5.1	Common indicators selected by focal area	2

5.2	Lessons learned related to indicators	2

6	Follow up work	2

7	Conclusions	2

References	2

Annex 2	Summary of Evaluation Responses	2

Tables

1	Objectives template	2

2	Draft objectives table IWP Cook Islands (November 2004)	2

3	Draft objectives table IWP Niue (November 2004)	2

4	Draft objectives table IWP Tonga (November 2004)	2

5	Monitoring plan template	2

6	UNDP Criteria for assessing indicators	2

7	Draft monitoring plan IWP Niue (November 2004)	2

8	Draft monitoring plan IWP Tonga (November 2004)	2

9	Draft monitoring plan IWP Cook Islands (November 2004)	2

10	Indicators commonly identified during monitoring workshops	2

11	Vague indicators and more specific alternatives	2

Boxes

1	First quarterly narrative report for IWP Tonga: monitoring section	2

# 1	Introduction

The Pacific International Waters Project (IWP) is a seven-year (2000-2006) regional project involving 14 participating countries: Cook Islands, Federated States of Micronesia, Fiji, Kiribati, Marshall Islands, Nauru, Niue, Palau, Papua New Guinea, Samoa, Solomon Islands, Tonga, Tuvalu and Vanuatu.

The project is funded by the Global Environment Facility (GEF), implemented by the United Nations Development Program (UNDP) and executed by the Secretariat of the Pacific Regional Environment Programme (SPREP). Day to day regional management of the project is conducted through a SPREP based project coordination unit (PCU) located in Apia while in-country management of IWP activities is coordinated by country-based officers, national coordinators (NCs).

The objective in the Integrated Coastal and Watershed Management (ICWM) component of the Project is to address root causes of identified threats to the international waters of the Pacific Islands region relating to:

- pollution of marine and freshwater (including groundwater) from land-based activities;

- modification of critical habitats, and

- unsustainable use of resources.

The Project Document (UNDP/GEF 1999) that describes the rationale and problem analysis for the IWP observes that these three identified threats to international waters are intimately connected to four focal areas in the small island environments of the Pacific:

- the management of coastal fisheries;

- the establishment of marine protected areas;

- the protection of freshwater resources; and

- effective management and reduction of waste.

Accordingly, the ICWM component of the project supports national and local level pilot activities to improve the management of coastal resources in these four ‘focal’ areas. It aims to strengthen environmental management at local, national and regional levels, drawing on lessons learned from previous initiatives as well as the experience in implementing its own pilot activities (see below).

### The ‘two pronged approach’

The Project seeks to improve the management of coastal areas and resources through a ‘two-pronged approach’ that targets pilot activities at the local and national level in each country.

At the local level, the project supports pilot activities in selected host communities (villages or sets of villages). The focus is to promote increased community involvement and responsibility for local resource management and conservation initiatives, recognising that Pacific communities have significant authority, control and systems of management over natural resources.

Of course, not all environmental problems can be solved by community action (local level activities) alone. Types of environmental issues that cannot be addressed at the local level include the cumulative impacts of resource degradation across several communities or regions (such as total catch levels or pollution from a number of villages), strategic and coordination issues (such as the need to manage multiple communities in a single management plan) and legislative and national enforcement issues.

Accordingly, those root causes for environmental problems that cannot or should not be addressed locally alone are addressed under the IWP at the higher (national and or regional) level. Therefore, the project also supports initiatives to address root causes on an island-wide or national scale. These activities can focus on issues such as policy or legislation development, enforcement or institutional arrangements contributing to root causes in the four focal areas.

From a monitoring perspective, this distinction between local and national level activities will be important in terms of the shape of monitoring plans and the types of indicators to be used.

### IWP project cycle

An important aspect of the coastal component of the IWP is the project cycle (figure 1) adopted to support continuous learning and adaptive management. The project cycle allows for a stepwise approach to describing and analysing environmental problems and assessing, implementing and evaluating solutions. Each step undertaken in the cycle is intended to build on the lessons and activities from the previous step so that resource management follows a logical path with a strong emphasis of learning.

From a monitoring perspective, the use of a project cycle is important for two reasons. First, continuous learning and adaptive management in projects hinges on the monitoring and assessment of projects so that appropriate refinements to project design and implementation can be achieved. This means that the selection of relevant indicators and their collection and analysis are critical.

Second, the sequence of activities in the IWP project cycle means that the identification of indicators naturally follows the identification of project activities. Nevertheless, and as will become evident in subsequent sections in this paper, there are distinct benefits and challenges to considering monitoring issues in the initial strategic planning stage to ensure that project activities and resulting indicators were properly linked to project goals and objectives.

Figure 1	Project cycle for the IWP pilot projects

# 2	Monitoring under the IWP

The GEF places a heavy emphasis on monitoring of IW projects. Duda (2002, p. 2) observed that:

... the GEF Council adopted an Operational Strategy that recognizes that the reversal of environmental degradation in complex transboundary freshwater or marine situations may take decades. It was acknowledged that a series of projects with progressive GEF involvement may be needed in a specific basin or marine ecosystem to leverage the needed country reforms and investments for adequately addressing transboundary water issues… Consequently, experience up to 1994 illustrated that different types of monitoring and evaluation indicators were needed for international waters interventions to show actual step-by-step progress toward the adoption of the joint management regimes, country-based reforms, and priority investments that are necessary precursors of improvements in water quality, quantity, or biological factors detectable in transboundary systems.

GEF IW projects are consequently expected to formally contain monitoring structures and processes that enable stakeholders to assess the progress in projects towards real outcomes. Furthermore, a mid term evaluation of the IWP (Hunnam and Schuster 2003) in 2003 recommended increased attention to monitoring and evaluation to:

- link national activities to the overall project log frame; and

- identify how pilot project activities were contributing to improving environmental status and reducing environmental stress.

# 3	Starting off the monitoring plan process

Considerable information exists throughout the literature on principles, frameworks and potential indicators for monitoring development processes. (See, for example, Olsen 2003, Belfiore 2003, Bowen and Riley 2003). In addition, the GEF has also provided some information on key issues for consideration when monitoring GEF projects (Duda 2002).

However, there was a general feeling in the SPREP PCU that assistance was needed to guide countries and SPREP together through the process of developing monitoring plans. This is because there was:

- limited time to review the plethora of existing approaches and information;

- a lack of good examples/templates available from the GEF from similar projects worldwide which could be used to develop plans to meet the specific needs of the Pacific IWP; and

- admittedly, limited experience in the IWP in applying formal monitoring frameworks to a GEF project.

To provide support, the SPREP-based PCU contracted a consultant to review relevant work on monitoring, develop a framework and train NCs in the development of monitoring plans. Terms of reference for the consultant are given in annex 1. The terms of reference essentially involve a review of monitoring literature of relevance to Pacific island and UNDP/ GEF environment and development projects, together with the conduct of training workshops with NCs and follow up work as necessary. Details of the work conducted and outcomes are given in Mahanty (2004a and 2004b).

## 3.1	Review of relevant work/information

Before considering how to identify indicators for the IWP or frameworks to adopt, the consultant reviewed a number of relevant monitoring processes and documents including:

- the overall project log frame and monitoring and evaluation plan for the Pacific IWP (GEF/UNDP 1999 and subsequent revisions);

- GEF guidelines for monitoring environment and development project (Duda 2002);

- UNDP criteria for effective indicators (UNDP 2002);

- IWP guidelines for IWP project implementation (PCU 2003);

- Lessons from previous attempts by SPREP to develop and implement monitoring activities in community based activities (such as through the South Pacific Biodiversity Conservation Programme);

- Supplementary material from sources such the World Bank, IDRC and academic literature (Bunce and Pomeroy 2003; Earle et al. 2001; Guijt and Abbot 1998; Lusthaus et al. 2000; Margoluis and Salafsky 1998; Pasteur 2001; Russell and Harshbarger 2003; Thorburn 2003).

The purpose in conducting this review was to ensure that the focus and objectives in the IWP monitoring program drew on best practice and current thinking in monitoring and evaluation while applying the GEF framework. This information provided the basis for discussions on how to approach monitoring, what kinds of indicators to target, how to collect, analyse and report on information collected as well as likely challenges. A review of work that underpins processes supporting the process ultimately developed for IWP monitoring purposes can be found in Mahanty et al. (forthcoming).

## 3.2	Dedicated planning workshops for the IWP

### Broad overview of workshops

Having reviewed relevant information, the consultant developed and facilitated two workshops to guide the development of monitoring plans for the IWP. Two workshops were conducted because, although only one 1.5 day workshop was originally envisaged (see Mahanty 2004a), NCs requested extra time and assistance to complete plans in a second dedicated meeting of national coordinators (see Mahanty 2004b).

### Monitoring workshop 1

Monitoring workshop 1 was conducted as a discrete 1.5 day component of the annual meeting of national coordinators (NCM) for the IWP. This monitoring workshop was intended to:

- refine an agreed project Log frame at the regional level and related monitoring and evaluation plan to take to the Multi-Partite Review immediately following NCM4 (facilitated by the Project Manager);

- develop NCs’ understanding of key monitoring concepts;

- develop NCs’ understanding of the GEF/UNDP framework for monitoring;

- develop generic examples of monitoring indicators for three focal areas, which could be adapted to specific projects; and

- assist NCs with initial development of their project monitoring plans (Mahanty 2004a).

The workshop was designed around the use of the GEF framework for monitoring, involving the use of process, environmental stress reduction and environmental status indicators (defined in section 5). The emphasis in the workshop was the identification and assessment of indicators that might be expected to adequately support in-country project goals/objectives/outcomes.

The workshop involved the following broad steps:

- presentation by the consultant on:

-	the meaning and purpose of monitoring and how it relates to indicators;

-	broad principles and components of monitoring and indicators under the GEF and UNDP;

- guided NC activities to develop a set of generic indicators for three focal areas that NCs could then draw on in developing their own monitoring plans. This involved the use of three hypothetical case studies that were based around conditions and issues relevant to three key focal areas being addressed in pilot projects (fisheries, waste management, freshwater resources management). NCs developed a set of monitoring indicators for these hypothetical projects;

- initial steps towards developing project monitoring plans for pilot projects, which involved:

-	completing templates to articulate in-country goals, objectives, outcomes and activities;

-	identifying relevant indicators in light of goals, objectives, outcomes and activities (drawing on the indicators developed in step 2);

-	identifying other (logistical) issues that might have a bearing on monitoring work, as appropriate.

### Monitoring workshop 2

Monitoring workshop 2 was conducted as a discrete 1 day component of an extra ordinary NCM. The workshop was intended to:

- further clarify the requirements of the GEF/UNDP monitoring framework;

- assist NCs to refine project goals, objectives, outcomes and activities; and

- assist NCs to revise and compile project monitoring plans.

The workshop involved the following broad steps:

- presentations by nominated 'champion’ NCs on the draft project monitoring plans they had so far produced. These presentations were intended to stimulate discussion on common challenges they faced in developing monitoring plans in practice;

- as necessary, refining in-country projects goals and objectives with support from the consultant and PCU staff;

- R\reviewing and refining indicators in light of any revisions to in-country project goals and objectives with support from the consultant and PCU staff; and

- completion of project monitoring plans, including identification of when and how specific indicators might be monitored, recognising that the plans would need further refinement and discussion with project stakeholders in-country.

# 4	Identifying project goals and objectives

The IWP recognises that monitoring is a process of tracking change and progress towards project objectives. In the workshops, an effort was made to support NCs develop monitoring plans that would help to assess in-country progress towards project goals, objectives, and desired outcomes.

Since project monitoring is ultimately about assessing progress towards project goals and outcomes, it goes without saying that project goals and objectives need to be articulated as a basis for monitoring. Nevertheless, in the IWP case, many countries had gravitated automatically towards certain activities, presuming that they were valuable (which they often were), without explicitly identifying the relationship between the activities selected and the overall goals of the project.

To assist NCs articulate their goals and their relationship to activities, they were encouraged to complete the template below (Table 1) outlining their goals, objectives, outcomes and activities. This ‘objectives table’, as it became known, provided the most critical step in the entire monitoring process as all monitoring plans hung from this. (It can be seen that effectively NCs were being asked to arrange their project activities into a log frame.)

#### 1	Objectives template

| Goal: |  |
| --- | --- |
| Objective: |  |
| Outcome 1 |  |
| Activity 1.1 |  |
| Activity 1.2 |  |
| Activity 1.3 |  |
| Outcome 2 |  |
| Activity 2.1 |  |
| Activity 2.2 |  |
| Activity 2.3 |  |
| Outcome 3 |  |
| Activity 3.1 |  |
| Activity 3.2 |  |

As the work of the IWP involves activities at both the local and national level, NCs generally divided up their project objective, outcomes and activities accordingly. Examples of draft objectives tables produced during the meeting are given in tables 2 to 4. Table 2 reflects the Cook Islands’ IWP focus on freshwater management and the protection of freshwater and coastal habitats. Table 3 reflects Niue’s IWP focus on coastal fisheries management through effort and habitat management. Table 4 reflects Tonga IWP’s focus on freshwater and coastal habitats through improved waste management.

#### 2	Draft objectives table IWP Cook Islands (November 2004)

#### 3	Draft objectives table IWP Niue (November 2004)

| GOAL: | To strengthen sustainable management of coastal resources |
| --- | --- |
|  | LOCAL PROJECT COMPONENT |
| Objective 1: | Strengthen capacity at Alofi North and Makefu to sustainably manage coastal fisheries. |
| Outcome 1 | Motivated stakeholders participating in coastal fisheries management arrangements. |
| Activity 1.1 | Establish, implement and manage a communication strategy for Alofi North and Makefu (posters, radio programmes, public education and awareness, etc). |
| Activity 1.2 | Stakeholder analysis and participation plan for Alofi North and Makefu. |
| Activity 1.3 | Complete a PPA (root cause assessment at Makefu and Alofi North). |
| Activity 1.4 | Assess solution options for addressing root causes for non-sustainable use of coastal resources at Makefu and Alofi North. |
| Activity 1.5 | Complete review of prior research literatures in relation to fisheries for Makefu and Alofi North |
| Activity 1.6 | Ecological baseline survey completed for Makefu and Alofi North |
| Activity 1.7 | Socio-economic baseline survey for Makefu and Alofi North |
| Activity 1.8 | Prepare a village profile |
| Outcome 2: | Strengthened local capacity to sustainably manage coastal fisheries at Makefu and Alofi North. |
| Activity 2.1 | Describe existing village governance arrangements (community structure) at Alofi North and Makefu |
| Activity 2.3 | Establish a Village Fisheries Management Committee Group in Makefu and Alofi North village (Local Project Working Group) and support regular meetings. |
| Activity 2.4 | Review options for strengthening village co-management arrangements to achieve sustainable coastal fisheries. |
| Activity 2.5 | Design and implement a local community coastal fisheries management plan (incorporating tools such as area rotation permanent closures system of harvesting using the ‘Fono’, and participatory monitoring, etc.). |
| Activity 2.6 | Select and train local facilitators to support participatory marine resource monitoring. |
| Outcome 3 | Options and alternatives for income generating opportunities |
| Activity 3.1 | Evaluate income generating opportunities to reduce fishing pressure for Makefu and Alofi North |
| Output 4 | Increased capacity at Makefu and Alofi North to manage the impacts of local land-based activities on the coastal environment |
| Activity 4.1 | Identify and engage partners to monitor impacts of land-based activities on the coastal environment at Makefu and Alofi North (water quality monitoring at coastal springs, etc) and report results to the communities and relevant Government agencies. |
|  | NATIONAL PROJECT COMPONENT |
| Objective 2: | Strengthen capacity at a national level to sustainably manage coastal fisheries. |
| Outcome 1 | Project implementation arrangements established |
| Activities 1.1 | Local project staff recruit, administrative arrangements (including information management) established |
| Activities 1.2 | National stakeholder analysis |
| Activities 1.3 | Establish a National Task Committee and service regular meetings |
| Activities 1.4 | Establish a Project Development Team and support regular meetings |
| Activities 1.5 | Undertake review of Priority Environment Concerns |
| Outcome 2 | Strengthened institutional capacity for coastal fisheries management |
| Activities 2.1 | Identify and train local facilitators to support participatory problem analysis (root cause) for coastal fisheries. |
| Activities 2.2 | Complete a profile of Government ministries |
| Activities 2.3 | Complete a national level assessment of root causes for non-sustainable coastal fisheries (Village Situation Analysis) |
| Activities 2.4 | Assess existing legislation and institutional arrangements relating to coastal fisheries management (including Coastal Fisheries Management Plan) and revise and strengthen arrangements as necessary. |
| Activities 2.5 | Undertake a training needs analysis for coastal fisheries management in DAFF Fisheries Division |
| Activities 2.6 | Support capacity building for DAFF Fisheries Division staff in coastal fisheries management |
| Activities 2.7 | Support implementation and monitoring of adopted Coastal Fisheries Management Plan including coordinating arrangements for VFMCs |
| Activities 2.8 | Identify and support initiatives to reduce fishing pressure on coastal resources (re-locate fishing effort off-shore) |
| Activities 2.9 | Identify and support initiatives to reduce national level impacts of land-based activities on the coastal environment |
| Outcome 3 | Project Communication Strategy implemented |
| Activity 3.1 | Design and implement a National Project Communication Strategy |

#### 4	Draft objectives table IWP Tonga (November 2004)

| Goal: | To improve management of waste on Tongatapu |
| --- | --- |
| Objective 1 | Improved capacity at Nukuhetulu village in managing their waste |
| Outcome 1 | Increased understanding of the causes and impacts of inappropriate waste disposal |
| Activity 1.1 | Conduct Stakeholder Analysis (completed) |
| Activity 1.2 | Conduct Participatory Problem Analysis (completed) |
| Activity 1.3 | Conduct Baseline socio-economic and waste characterisation survey (completed) |
| Activity 1.4 | Conduct water quality baseline survey |
| Activity 1.4 | Implement local component of the Communication Strategy (including local management plan) |
| Outcome 2 | Increased recycling of waste in Nukuhetulu village |
| Activity 2.1 | Set up village project committee (completed) |
| Activity 2.2 | Conduct compost training workshop (completed) |
| Activity 2.3 | Establish household compost and home gardening demonstration and set up incentives |
| Outcome 3 | Improved Water Quality (groundwater and lagoon) at Nukuhetulu village |
| Activity 3.1 | Conduct pesticide awareness and sustainable agriculture workshop (completed) |
| Activity 3.2 | Set up demonstration plot for organic and low chemical farming |
| Activity 3.3 | Conduct feasibility study on cost effective/appropriate sanitation system to replace pit toilet (demonstration) |
| Activity 3.4 | Develop and implement as appropriate a Nukuhetulu Waste Management Plan (animal, composting, rules, monitoring) |
| Activity 3.5 | Train facilitators on water quality monitoring techniques |
| Objective 2 | Improve national capacity to manage waste |
| Outcome 4 | Strengthened national capacity in management of waste in issues |
| Activity 4.1 | Set up NTF and related technical sub-committees & hold regular meetings |
| Activity 4.2 | Establish partnerships with other programs/projects dealing with waste management |
| Activity 4.3 | Award scholarships to research students on topics related to waste management |
| Outcome 5 | Legislative and policy reform |
| Activity 5.1 | Review legislation and policies related to waste management in Tonga |
| Activity 5.2 | Draft and implement legislative and policy amendments |
| Outcome 6 | Improve awareness of waste management issues |
| Activity 6.1 | Conduct Economic Evaluation of waste in Tongatapu |
| Activity 6.2 | Implement the national component of the communication strategy |

## 4.1	Lessons learned related to goals and objectives

Establishing the goals and objectives of in-country projects turned out to be the most difficult aspect in developing monitoring plans in the IWP for a variety of reasons:

- Although NCs had previously been provided with the log frame for the IWP and have been asked to consider it in light of their in-country work, this was the first time that some of them actually considered a log frame for their own projects.

- It was the first time that many NCs had tried to articulate their own project goals, objectives, outcomes and activities. Many coordinators had presumed the value of their activities but had not explicitly considered how one activity linked to another, and how goals were supported by specific objectives, which were in turn supported by relevant activities.

- In many cases, NCs had intuitively adopted multiple goals for their projects and it became difficult to map the relationship between goals/ objectives, prioritise them and relate specific activities to these.

Ideally, IWP countries should have specified goals and objectives before identifying in-country activities so that all activities could be clearly linked in advance. However, in practice, the IWP experience is that countries frequently wanted to have project activities firmly in mind/ underway before they were able step back and identify a broad pathway.

Although time consuming, the process of clarifying (or even identifying) goals, objectives, outcomes and activities therefore turned out to be a highly beneficial process for the IWP. Most NCs found the exercise highly valuable in terms of:

- clearly linking local and national level activities (the two–pronged approach) to addressing root causes; and

- streamlining their projects and containing the focus of their work.

For example, where projects were targeted to address multiple focal areas, the monitoring process highlighted the importance of ensuring that different project components complemented each other and addressed the same goal. Thus, as Leah Nimoho, the national coordinator for IWP Vanuatu observed:

When we started on the IWP, we decided that we wanted to address two focal areas at once – freshwater and fisheries to address integrated watershed management. The PCU asked us at the time how these two focal areas linked together and would address the same goal. They asked whether we wanted to focus on only one focal area instead to keep things clearer. However, we were determined to address both issues. When we came to the monitoring process, however, we finally understood what they were saying about how these different areas complemented each other and addressed the same issue. In fact, after trying to strategically link the two areas and consider activities and monitoring issues, we decided to drop the freshwater component of the project and focus specifically on fisheries as the project made more sense this way (Leah Nimoho, IWP Vanuatu, personal communication 21 July 2005).

The monitoring process accordingly streamlined some projects and subsequently enabled identification of more targeted indicators. Because links between local and national activities were much clearer, NCs were also better able to communicate their work to the local stakeholders and in the local and regional media.

# 5	Identification of indicators

NCs were introduced to the three different types of indicators recommended by the GEF:

- Process indicators: these are indicators that measure progress with implementation of project activities and the establishment of supportive processes to support the achievement of project goals, such as participation and collaborative processes and mechanisms, capacity building, review and amendment of legislation, and development of management plans;

- Environmental stress reduction indicators: these are indicators that measure actual on the ground changes in actions and behaviours that address environmental threats, such as enforcement of legislation and resource management rules, evidence of increased stakeholder awareness, behavioural change for example in harvesting techniques and rates, and increase in areas under effective management or protection; and

- Environmental status indicators: these are indicators that measure actual success in environmental outcomes such as improvements in ecological or biological conditions, improvements in water quality, improvements in social conditions (which should not be worsened, but preferably improved), and recovery of flagship or indicator species. (Duda 2002).

It was noted during the workshops that stress reduction indicators are more likely to be the main focus of monitoring plans during the remaining two years of the IWP, while changes in environmental status would typically occur over a longer timeframe and be influenced by many factors beyond the project. However it would still be necessary to have the relevant baseline information on environmental status and to factor these indicators monitoring into plans to meet GEF guidelines. In addition it was suggested that most projects would probably have more process indicators than stress reduction indicators since the supportive processes and actions for the project were typically more numerous than the key changes being promoted in projects.

NCs worked in groups to identify process, environmental stress reduction and environment status indicators for hypothetical projects in three key focal areas that might generally be relevant to their projects. Subsequently, they were invited to complete a ‘monitoring plan template’ (table 5) in light of their objectives tables and drawing on the indicators developed in groups. The monitoring plan template guided NCs to identify two or three process and stress reduction indicators for each outcomes, together with two or three environmental status indicators for the entire project.

As many NCs enthusiastically identified numerous indicators, they were encouraged to limit the number of nominated indicators to avoid excessive monitoring loads. (This is particularly relevant where communities were being asked to conduct monitoring activities.) Accordingly, NCs were referred to a list of UNDP criteria (table 6) to help them select around ten to twelve indicators overall for their monitoring plans, including:

- one to five process indicators per outcome

- one to five stress reduction indicators per outcome; and

- two to three environmental status indicators per project.

Examples of draft monitoring plans produced during the meeting are given in tables 7 to 9. Table 7 builds on IWP Niue’s objectives table (Table 3). Table 8 builds on IWP Tonga’s objectives table (Table 4). Table 9 builds on IWP Cook Islands’ objectives table (Table 2).

#### 5	Monitoring plan template

| Outcome | Indicator | Source of verification (evidence) | Timing of data collection (when) | Frequency (how often) | Who does the monitoring (who) | Who are the results for? (audience). | Estimated Cost? |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 |
| Process Indicators (no more than 5-10) | PI 1. |  |  |  |  |  |  |
|  | PI 2. |  |  |  |  |  |  |
|  | PI 3. |  |  |  |  |  |  |
|  | PI 4. |  |  |  |  |  |  |
|  | PI 5. |  |  |  |  |  |  |
| Environmental Stress Reduction Indicators (no more than 5-10) | ESRI 1. |  |  |  |  |  |  |
|  | ESRI 2. |  |  |  |  |  |  |
|  | ESRI 3. |  |  |  |  |  |  |
|  | ESRI 4. |  |  |  |  |  |  |
| Outcome 2 |
| Process Indicators | PI 1. |  |  |  |  |  |  |
|  | PI 2. |  |  |  |  |  |  |
|  | PI 3. |  |  |  |  |  |  |
|  | PI 4. |  |  |  |  |  |  |
|  | PI 5. |  |  |  |  |  |  |
| Stress Reduction Indicators | ESRI 1. |  |  |  |  |  |  |
|  | ESRI 2. |  |  |  |  |  |  |
|  | ESRI 3. |  |  |  |  |  |  |
|  | ESRI 4. |  |  |  |  |  |  |
|  | ESRI 5. |  |  |  |  |  |  |
| Outcome 3 |
| Process Indicators | PI 1. |  |  |  |  |  |  |
|  | PI 2. |  |  |  |  |  |  |
|  | PI 3. |  |  |  |  |  |  |
|  | PI 4. |  |  |  |  |  |  |
|  | PI 5. |  |  |  |  |  |  |
| Stress Reduction Indicators | ESRI 1. |  |  |  |  |  |  |
|  | ESRI 2. |  |  |  |  |  |  |
|  | ESRI 3. |  |  |  |  |  |  |
|  | ESRI 4. |  |  |  |  |  |  |
|  | ESRI 5. |  |  |  |  |  |  |
| Environmental Status Indicators for Project (no more than 3) | ESI 1. |  |  |  |  |  |  |
|  | ESI 2. |  |  |  |  |  |  |
|  | ESI 3. |  |  |  |  |  |  |

#### 6	UNDP Criteria for assessing indicators

The meaning of the indicator is clear.

Data are easily collected.

Effort to collect the data is within the power of the project team and community and does not require experts for analysis.

Indicator is sufficiently representative for the total of the intended results.

Indicator is tangible and can be observed.

Indicator is difficult to quantify but it is so important that it should be considered (proxy indicator).

Source: UNDP (2002).

#### 7	Draft monitoring plan IWP Niue (November 2004)

| Output | Indicator | Source of verification | Specific meaning | Ease of data collection | Who collects the data | Cost NZ$ |
| --- | --- | --- | --- | --- | --- | --- |
|  | LOCAL LEVEL |  |  |  |  |  |
| (1) Establishments of Working Groups: To achieve social accountability services to effectively support co-management of coastal resources. (Demonstrate resource ownership). National Institutions are strengthened to support sustainable coastal fisheries management. | Applicable Term of References (TOR) are developed and agreed to by parties, National working groups including NTC (NTC) and Project Development Team (PDT) and Local Project Working Groups (LPWG) are established, Establish a Village Group to work with Village Councils in affairs related to co-management of coastal fisheries, Village social structures indicate diversity for stakeholder groups to support relative villages affairs including resource base projects, National level is committed to development strategies that villages can approach for support. | Project Memorandum of Understanding verifies TOR for NTC, TOR verifies tasks for the Project Development Team, Term of Reference is established for the Local Project Development Team, Village Profiles, Government Profiles, | Yes Yes Yes Yes Yes | Ease Ease Medium Ease Ease | Village Councils, Local Project Working Group DAFF Environment Department Community Affairs Premiers Department | $6,000.00 (2004-2006) |
| (2) Marine Protected Area: Declare Vailoapu-Namoui Marine Protected Area and By-law to preserve overall resource biodiversity as a heritage. | Indication of fishing still carried out in the Marine Protected Area, Villages indicated in village meetings need to strengthen their role in managing the Marine Protected Area, Villages submitted request indicating Expression of Interest for legal assistances to establish village-based co-management systems. | Fishing gear was observed in the Marine Protected Area, Letters from Village and Meeting documents Existing legislations verifies support to develop village legal authority, | Yes Yes Yes | Ease Ease Medium | Villages Councils, Local Project Working Groups, Crown Laws Office, DAFF Cabinet | $2,000.00 |
| (3) Public Awareness: Deploy public awareness campaigns possible to change social behaviour impacts causing resource degradation. | People in village meetings indicated weakness in awareness to remind and keeping the public informed, Indication of development impacts (e.g. sea tracks) are in a accelerating trend as measured with coastal resource management, Increasing ease availability in modern sophisticated gear types and fishing practices is an indication risk to overfishing. | Verified by level of awareness materials locally produced, Development strategies in the national strategic plan have minimal progression to parallel with sustainable commitments, Set nets, torches, hammers, axes are used uncontrolled to harvest and increase catches. | Yes Yes Yes | Yes Medium Medium | Village Councils, Local Project Working Group, PCU, SPREP DAFF, Environment Department Health, Water Supply. | $22,250.00 |
| 4) Village Capacity Building: To achieve specialised skills and setting up stakeholder’s capacity to monitor the reef flat targeted species. | Villages expressed concerns and uncertainties related to the resource status presuming resources are degrading based on low level catches Villages recognised that catches have decreased over the years. | Concerns are verified in the Village Situation report covered during the participatory problem analysis phase Preliminary Baseline Survey provides data to verify status and applications for resource monitor, | Yes Yes | Medium Medium to High | Village Councils, Local Project Working Group, DAFF. | $30,000.00 |
| 5) Income Generating: Implement other alternatives for income generating actions to achieve returns from resources in a sustainable and responsible manner and remove pressures off the reefs. | Villages are concerned that if management plans should result in area closures or restricted harvests other beneficial alternatives should be explored like in tourism, Efforts to remove the fishing pressures off the reefs may indicate interests in the offshore fishery, | Area Closures in Declaring the Marine Protected Area reduces fishing area for the villages, Fishing offshore is a national interest to target the migratory species. | Yes Yes | Ease Medium to High | Village Councils, Local Project Working Group, Tourism, DAFF. | $1,000.00 |
| 6) Niue Fish Management Plan: To adopt policies and implement overall effective management policies. | * Indicated by the National Management Plan developed for Niue. | Verified by national stakeholders consultations. | Yes | Medium | Village Councils, Local Project Working Group, DAFF, | $55,000.00 |
| 7) Marine Protected Area Look out track, road signs and shelters: Provide access or scenic spot, awareness and platform to police Marine Protected Area. | Meeting between the village representatives and government technical advisors identified requirements under output 7 as a immediate need, | Meeting proceedings record, | Yes | Ease | DAFF Village Councils Local Project Working Group | $2,000.00 |
| 8) Fish Poisoning (Ciguatera): Cautioning the general public of symptoms and effects caused from fish poisoning. | Concerns expressed by Alofi North village expressing uncertainties and extend of fishing poisoning in village vicinity. | People reported sick from fish poisoning, | Yes | Medium | Village Councils, Local Project Working Group, Health Department | $500.00 |
| 9) Village Base Fish Management Plan: Achieve a guided action plan for the villages to use to manage and administer management actions in the villages. | Management Plan is part of the overall framework that the pilot project is envisaged to demonstrate and develop, | Verified by the success of the pilot project, Village meetings to complete village-base fishery management plan | Yes | Medium | Village Councils, Local project Working Group, DAFF, Environment Department Community Affairs, Education | $600.00 |
| 10) Legislation: Safety for canoes and small boats (Monitor that actions are carried out) | Villages raised concerns that small outboard run fishing boats are too close to canoes causing problems for safety at sea, | Verified in Meetings, Near accidents occurring involving canoes and dinghies. | Yes | Ease | Village Councils, Local Project Working Group, Crown Laws Office. | Legislation review, |
| 11) Coastal Planting: Protect reef ecosystems from land-base erosion. | Environment Department under the national strategic plan is responsible to organise a national tree planting day, DAFF indicated supplies of plants to assist the tree planting activities in the villages. | National Strategic Action Plans states need for a national tree planting day, Villages met with government technical advisors | Yes Yes | Ease Ease | Village Councils, Local Project Working Group, Environment Department DAFF. | $1000.00 |
| 12) Ballast Water Discharges: Eliminate Ballast Water discharged near shore. | Public are uncertain of the ballast water and procedures of discharges. | Data unavailable to support claim for uncontrolled ballast water discharges | Yes | Ease | Crown Law, Port authorities, | $1,000.00 |
| 13) Environment Impact Assessments (EIA): Conduct EIA prior to any development. | EIA can be considered as not a priority pose to development progress. Just recently a fish process plant was constructed without an EIA conducted. | No EIA is verified by poor drainage systems causing siltation and runoffs. | Yes | Ease | Environment Department Village Councils, Local Project Working Group. | $500.00 |
| 14) Baitfish Fish Aggregation Devices (FADs): Remove pressures off the reefs and entice baitfish near shore. | Local preferred bait fish are not available most time of the year to target the offshore fishery. | Villages complaining about Fish Aggregation Device deployed too far out effecting good access for baitfish. | Yes | Medium | Village Councils, Local Project Working Group, DAFF, NGOs, canoes and small boats | $4,000.00 |
| 15) Catch Log: To achieve species catch information. | Fish catch data programs is depending on national capacity, Indications of village-base co-managing data is to be tested out. | Villages setting up of resource centres in the villages and instalment of electronic data bases, | Yes | Medium to High | Village Councils, Local Project Working Group, NGOs DAFF | $500.00 |
| 16) Coastal freshwater monitoring: To monitor quality of freshwater | Public uncertainty in freshwater quality (Village situation report) Fresh water is commonly seen seeping out around the reefs, | Meetings Documentations/reports | Yes Yes | Medium to High Ease | Village Councils Local Project Working Group Water Supplies | $32,800.00 |
| 17) Waste Management: |  |  |  |  |  |  |

#### 8	Draft monitoring plan IWP Tonga (November 2004)

| Indicator | Source of verification (evidence) | Timing of data collection (when) | Frequency (how often) | Who does the monitoring (who) | Who are the results for? (audience). | Estimated Cost? (TOP) |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1a: Improved capacity of Nukuhetulu village in managing their waste |
| Outcome 1: Increased understanding of the causes and impacts of inappropriate waste disposal |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Stakeholder analysis completed | Stakeholder Analysis Report | Completed | Twice | NC/PCU | NTF/ Community | None |
| PI 2. Selection of Tonga’s Priority Environment Concern | PEC Report | Completed | Once | NC/PCU | NTF | None |
| PI 3. Participation of relevant stakeholders in Problem Analysis | PPA Report | Completed | Once | NPDT/ Community | NTF Community | 8000.00 |
| PI 4. Baseline socio-economic and waste audit for Nukuhetulu village completed | Baseline Socio Economic and Waste Audit Report | Completed | Yearly | NPDT/ Community | NTF/NPDT Community | 17,000.00 |
| PI 5. Economic Evaluation of Waste in Tongatapu completed | Economic Evaluation of Waste Report (incl. Scoping Report) | Dec 04 | Once | consultants | NTF/NPDT Community | 40,000.00 |
| PI 6. National Communication Strategy completed | National Communication Strategy Report | Dec 04 |  | NC/PCU | NTF/NPDT Community |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. # of relevant stakeholders actively engaged in pilot activities | Meeting attendance record MOU & contract signed |  |  |  |  |  |
| ESRI 2. # of codes of conduct adopted by stakeholders | code of conduct meeting records |  |  |  |  |  |
| ESRI 3. # of funding partnership established to invest in IWP initiatives | MOU correspondence |  |  |  |  |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| EI 1. Improved understanding of root causes waste management |  |  |  |  |  |  |
| EI 2. |  |  |  |  |  |  |
| Outcome 2: Improved capacity of Nukuhetulu village in managing household organic waste |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Compost Training Workshop conducted | workshop report | Completed |  | NC/TCDT | Community |  |
| PI 2. Establishment of a Village Working Committee | Village meeting minutes | Completed |  | NC/LA/ NPDT | NTF/ Community/ donors |  |
| PI 3. Establish 10 household compost and home garden trial | observation photograph | Completed | 6 monthly | NPDT/ TCDT/ VWSC | NTF/ Community/ donors |  |
| PI 4. Conduct competitions on h/hold compost and home garden | competition flyer judges scoring record | Dec 04 | 3-6 monthly | NPDT/ TCDT/ VWSC | NTF/ public/ donors |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. # of people from community participate in the compost training & demonstration | workshop participants list TV news/newsletter | completed | When required | NC/PCU | NTF/ donors |  |
| ESRI 2. # of village working committee meeting & % attendance | meeting minutes photograph/newsletter |  | Bi-monthly | NC/LA | NTF/ community/ donors |  |
| ESRI 3. High % success from the 10 household demonstration compost | observation MOU signed and followed TV news/newsletter |  | monthly | TCDT/ VWSC | NTF/ public/ donors |  |
| ESRI 4. Increase # of new compost and home garden registered for competitions | observation/newsletter judges scoring forms | Oct 04 | Monthly inspection | TCDT/ VWSC | NTF/public/ donors |  |
| ESR! 5. Reduction in % of organic waste generated at household level | household monitoring survey report | Dec 04 | yearly | NPDT/ VWSC | NTF/public/ donors |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| EI 1. Improve capacity of local village in managing household organic waste |  |  |  |  |  |  |
| Outcome 3: Reduced chemicals use for subsistence farming |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Pesticides awareness workshop conducted | workshop report TV news/newsletter | Completed | Yearly | NC/TCDT/ VWSC | Community/ donors |  |
| PI 2. Community demonstration plot is completed and managed by the village working group | observation photograph/newsletter newspaper clips | Completed | Yearly | NC/TCDT/ VWSC | Community/ public/ donors |  |
| PI 3. Village code of conduct for organic farming practices agreed to by farmers | code of conduct for organic farming | Dec 05 |  | NPDT/ VWSC | NTF/ Community/ donors |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. Reduction in # of farmers using pesticides | h/hold monitoring survey report | Dec 04 | yearly | VWSC | NTF/farmers/ public |  |
| ESRI 2. # of penalties for breaching code of conduct | village working committee meeting minutes | Dec 05 | monthly | VWSC | NTF/farmers/ public |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| ESI 1. Improvement in community diet and health |  |  |  |  |  |  |
| ESI 2. Improvement in water quality |  |  |  |  |  |  |
| Outcome 4: Improved sanitation at Nukuhetulu village by replacing pit toilet |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Feasibility study for a viable h/hold sewage system completed | Feasibility study report | Jan 05 | Once | NC/ PCU/ consultant | NTF/NPDT/ VWSC/ donors |  |
| PI 2. Secure co-funding partners to replace pit toilet with a viable h/hold sewage system | Funding/Partners Proposal MOU signed | Jun 05 | Once | NC/PCU/ VWSC | Community/ donors |  |
| PI 3. Code of conduct on h/hold sewage disposal endorsed by relevant stakeholders and HM Cabinet | Code of conduct for household sewage disposal Cabinet submission and decision | Jan 06 | Once | NC/PCU/ VWSC | Community/ donors |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. Reduction in # of pit toilet at Nukuhetulu | H/hold monitoring survey report | Dec 05 | yearly | NPDT/ VWSC | NTF/public/ donors |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| ESI 1. Improvement in sanitation and health |  |  |  |  |  |  |
| Outcome 5: Improved grey-water treatment system at Nukuhetulu village |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Feasibility study for a viable grey-water h/hold disposal system completed | Feasibility study report | Jan 05 | Once | NC/ PCU/ consultant | NTF/NPDT/ VWSC/ donors |  |
| PI 2. Secure funding partners to establish viable h/hold grey-water disposal system | Funding/Partners Proposal MOU | Jun 05 | Once | NC/PCU/ VWSC | Community/ donors |  |
| PI 3. Code of conduct on proper h/hold grey-water disposal system endorsed by relevant stakeholders and HM Cabinet | Code of Conduct for household grey-water disposal | Jun 06 | Once | NC/PCU/ VWSC | Community/ donors |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. Increase in # of h/hold practising the introduced grey-water disposal system | H/hold monitoring survey report | Dec 05 | yearly | NPDT/ VWSC | NTF/public/ donors |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| ESI 1. Improvement in water quality |  |  |  |  |  |  |
| ESI 2. |  |  |  |  |  |  |
| Outcome 6: Improved management of roaming animals |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Pigs pence competition conducted | Competition flyer Judges scoring forms | Oct 04 | 3-6months | VWSC | Community/ NTF/ donors |  |
| PI 2. Animal control legislation has been reviewed | Reviewed legislation | Dec 04 | once | consultant | NTF/ Community/ donors |  |
| PI 3. Village rules/code of conduct and enforcement mechanism has been endorsed | Village rules | Dec 05 | once | NPDT/ VWSC | NTF/ Community/ donors |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. Decrease in # of roaming animals per household | Observation H/hold survey | Dec 04 | monthly | VWSC | NTF/ Community/ donors |  |
| ESRI 2. # of punishment for breaking the village rules | VWSC meeting minutes | Jan 06 | monthly | VWSC | NTF/ Community/ donors |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| ESI 1. Improvement in village aesthetic and health |  |  |  |  |  |  |
| ESI 2. Improvement in water quality |  |  |  |  |  |  |
| Outcome 7: Improved water quality (ground water and lagoon) at Nukuhetulu village |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Baseline water quality testing complete | Water quality testing report | Dec 04 | 6 monthly | Local consultant | Community/ NTF/ donors |  |
| PI 2. Local facilitators trained on monitoring technique | Contracts signed by local facilitators | Dec 04 | 6 monthly | Local consultant | Community/ NTF/ donors |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. Decrease over time in % of nutrients presence in the lagoon/ground water | Water quality monitoring report | Jun 05 | 6 monthly | Local consultant | Community/ NTF/ donors |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| ESI 1. Improved water quality (both lagoon and ground water) | water quality monitoring report | Dec 06 |  |  |  |  |
| ESI 2. Improved local capacity in monitoring water quality | water quality monitoring report | Dec 06 |  |  |  |  |
| Outcome 8: Improved local capacity in managing ground water resources |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Feasibility study of ground water management completed | Feasibility study report | Jan 05 |  |  |  |  |
| PI 2. Training of Village Water Committee (VWC) completed | Training report |  |  |  |  |  |
| PI 3. Secure funding partners and establish user-pay system | Funding proposal MOU |  |  |  |  |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. Increase in % of household paying for water use | Payment slip |  |  |  |  |  |
| ESRI 2. Less % water leaking | Water usage record balancing with financial record |  |  |  |  |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| ESI 1. Improve local management of ground water | Village Water Committee meeting minutes |  |  |  |  |  |
| ESI 2. Sustainable harvesting of ground water | monthly payment record |  |  |  |  |  |
| Outcome 9: Improved capacity of IWP National Task force in addressing waste issues |
| Process Indicators |  |  |  |  |  |  |
| PI 1. NTF and related project sub-committees established | Cabinet Proposal and Decision Meeting minutes MOU | completed |  |  |  |  |
| PI 2. NTF Capacity building needs assessment completed | Capacity building report |  |  |  |  |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. # of NTF and sub-committee meeting | Meeting minutes |  |  |  |  |  |
| ESRI 2. High % rate of meeting attendance | Meeting minutes |  |  |  |  |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| ESI 1. Improved coordination among stakeholders at different levels in addressing waste issues |  |  |  |  |  |  |
| ESI 2. |  |  |  |  |  |  |
| Outcome 10: Legislative and policy reform |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Legislative review completed | Legislation review report |  |  |  |  |  |
| PI 2. Draft Bill completed | Draft Bill |  |  |  |  |  |
| PI 3. Media campaign on legislative amendment | Media plan |  |  |  |  |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. # of new policies and bill addressing waste management | Cabinet submission |  |  |  |  |  |
| ESRI 2 |  |  |  |  |  |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| ESI 1. |  |  |  |  |  |  |
| ESI 2. |  |  |  |  |  |  |
| Outcome 11: Strengthened national capacity in management of waste in Tonga |
| Process Indicators |  |  |  |  |  |  |
| PI 1. Institutional arrangements completed | Institutional arrangements report |  |  |  |  |  |
| PI 2. Local facilitators trained | Local facilitators contract Training program |  |  |  |  |  |
| PI 3. Scholarship awarded | Scholarship agreement Research Thesis |  |  |  |  |  |
| Environmental Stress Reduction Indicators |  |  |  |  |  |  |
| ESRI 1. # of partnership established | Project report Institutional arrangement |  |  |  |  |  |
| ESRI 2. # of local facilitators trained and engaged in project activities | Contract |  |  |  |  |  |
| ESR 3. # of scholarship students graduated |  |  |  |  |  |  |
| Environmental Status Indicators |  |  |  |  |  |  |
| ESI 1. Improved national capacity in addressing waste management |  |  |  |  |  |  |
| ESI 2. |  |  |  |  |  |  |

#### 9	Draft monitoring plan IWP Cook Islands (November 2004)

| Indicator | Source of verification | Timing of data collection (when) | Frequency (how often) | Who does the monitoring | Who are the results for (Audience) | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Freshwater Management plan developed |
| Process Indicators |  |  |  |  |  |  |
| PI 1 Action Plan for the development of the Freshwater management plan developed | Action Plan | November 2004 | Once | NC & ANC, Community | NC & ANC, NTF, PCU, Community |  |
| PI 2 Management Plan developed, endorsed and legalized for implementation | Management Plan | May 2005 | Once | Community, IWPCOOKS | Community, IWPCOOKS, PCU |  |
| Stress Indicators |
| SI 1 No tramping without tour or community guide | Tour guide register | June 2005 | ongoing | Community | Community, IWPCOOKS |  |
| SI 2 No more domestic animals in the catchment | Community records | June 2005 | Ongoing | Community | IWPCOOKS, Community |  |
| Outcome 2 Freshwater Management Plan Implemented |
| Process |
| PI 1 Community structure and protocols revived and endorsed | Structure on paper signed by community leaders | November 2004 | Once | Community, and Community leaders | Community, government and the general public |  |
| PI 2 Community communication plan Implemented (on the management Plan) | Community Communication plan | April 2005 | Until October | NC & ANC | Takuvaine Community |  |
| Stress |  |  |  |  |  |  |
| SR 1 Community construct toilet and install bin below water intake | Toilet and Bin, Photo | November 2004 | Once | Community | IWPCOOKS, community and the general public |  |
| SR 2 People seen entering the restricted catchment area without authorization are fined | Offenders record book (observed, warned, fined) | April 2005 | On going | Village Committee, NC, ANC | Takuvaine Community, IWPCOOKS |  |

| National |
| --- |
| Outcome 1 National Management plan developed |
| Process |
| PI 1 National Freshwater Management Plan completed, endorsed, and legalised | Management Plan | September 2005 | Once | IWPCOOKS | IWPCOOKS, Community project committee, community |  |
| Stress |  |  |  |  |  |  |
| SI 1 Rarotonga catchment areas zoned | Lands and Survey records | May 2006 | Once | IWPCOOKS | IWPCOOKS, Government, Rarotonga Public |  |
| Outcome 2 National Management Plan Implemented |
| Process |  |  |  |  |  |  |
| PI 1 National Monitoring and coordination agency established | Rarotonga Freshwater Management Plan | September 2005 | Once | IWPCOOKS | Government, General Public |  |
| Stress |  |  |  |  |  |  |
| SI 1 Tourist accommodators promote management plan rules | Brochures, Posters | September 2005 | Bi-monthly | IWPCOOKS, Tourist Authority | IWPCOOKS, PCU |  |
| SI 2 Village Councillors and Village leaders implement and monitor rules at village level | Records of monitoring and of offenders (observed, warned, and fined) | September 2005 | Quarterly | Village Councillors | IWPCOOKS, general public |  |
| Status Indicator |
| STI 1 Takuvaine Faecal coliform level decreases | Test results | December 2005 | Monthly monitoring | Department of Water works, Public Health | IWPCOOKS |  |
| STI 2 Number of bottled water sold decreased | Shops in the village record | May 2006 | Monthly | NC & ANC | IWPCOOKS, PCU, community |  |
| STI 3 Water related illnesses down | Hospital Record | May 2006 | Three monthly | Public Health | IWPCOOKS, general Public |  |

## 5.1	Common indicators selected by focal area

By the time the workshops on the development of monitoring plans ended, most but not all monitoring plans had been progressed to varying extents. In any event, all countries took home draft plans to discuss with stakeholders. This was important to address any differences in opinion as to the goals and objectives in projects or the practicality of plans.

Common indicators identified by NCs are shown in table 10. (Note that the process indicators in part reflect key activities completed under the strategic planning and design phase of the IWP project cycle. This includes, for example, participatory analysis work, consultations with stakeholders and baseline work.)

#### 10	Indicators commonly identified during monitoring workshops

| Process | Participatory work completed and reported Baseline work completed and reported specific target groups (locals etc.) trained in x stakeholder analysis completed and reported revised legislation endorsed/passed codes of conduct/ new rules/ new management plans introduced |
| --- | --- |
| Stress reduction indicators | increased number of households/ people conducting composting increased number of households/ people sorting waste/recycling decreased breaches in rule x/ increased number of people complying with rule x increased number of people attending awareness/action meetings |
| Environmental status indicators | increased number of species x observed decreased level of faecal coliform in water samples decreased number of diarrhea/ typhoid etc cases reported |

## 5.2	Lessons learned related to indicators

Despite efforts to encourage NCs to limit the number of indicators to be used, some NCs identified a wide range of items to monitor. This produced some draft monitoring plans that required refinement. For example, one country produced complete monitoring plans on each seven key aspects of its project work. Needless to say, this approach led to considerable duplication across all of its monitoring plans and the likely burden of monitoring would have been excessive in terms of cost and resources required. Accordingly, follow up work was conducted with all NCs to ensure that monitoring plans were refined after the workshops and synthesised or focused as necessary.

A challenge for some countries developing indicators for project work was the lack of clarity in the indicator selected. Frequently, indicators were expressed using vague terms such as ‘improved’ without specifying precisely what was meant or how this would be measured/verified. Examples of non specific indicators nominated (and therefore difficult to verify) are shown in table 11.

#### 11	Vague indicators and more specific alternatives

| Vague indicator | Alternative indicators |
| --- | --- |
| Improved local management of fishery/waste/water | Improved compliance with existing/new rules Number of people trained in development and implementation of new rules Introduction of new village rules |
| Improved quality of water | Reduced level of faecal coliform |
| Improved health quality | Reduced incidence of diarrhoea/ typhoid/ dengue fever Reduced incidence of skin/ear infections |
| Improved understand of marine environment/how waste impacts health etc | Number of training/ awareness sessions conducted with high attendance Number of people changing from a destructive fishing practice to an appropriate practice Number of people using appropriate toilet systems |
| Improved health of fisheries/freshwater ecosystems | Increased number of species x and y observed Reduced level of faecal coliform in water samples |

The importance of accurate and relevant baseline information was highlighted during the development of monitoring plans. Although most countries participating in the IWP had already conducted, started or planned baseline work to support in-country activities, it became clear that the baseline work for some countries was or would be insufficient to meet monitoring needs. For instance, some countries concerned with protecting habitats by preventing pollution realised that they had not planned to collect baseline data on existing water quality before starting corrective activities. Without this information, it would be impossible to track whether water quality was consequently improving (let alone whether any changes were related to project activities). It also became apparent some countries who had completed baseline work did not consider their baseline information when identifying their indicators.

In light of the draft monitoring plans developed, countries generally reviewed their baseline information needs and many ended up building baseline data collection activities into their work plans. Consequently, some process indicators were identified to reflect the completion of additional baseline work. In a sense, the monitoring plans became a work plan for NCs to implement environmental work.

Another key issue in relation to baselines was the value of baseline studies as part of any situation analysis informing project design. While it is important for baseline information activities to have regard to monitoring plans, they need not be limited to these elements or variables. For example, in the Marshall Islands, where a very broad social assessment of host communities was conducted as part of baseline studies, important social issues were identified that were important both to the IWP project and in identifying priority areas for further action beyond the IWP.

# 6	Follow up work

The workshops resulted in the generation of draft monitoring plans for project activities across participating IWP countries. It was recognised early in the piece that the plans were only draft because:

- further work might be needed in-country to finalise and adopt the plans. As noted, for example, draft plans would at least need to be discussed with local and national stakeholders to ensure that they met the right goals and objectives and to ensure that they were realistic;

- some indicators would ultimately turn out in practice to be impractical to monitor or other indicators would emerge and take precedence.

For instance, follow up consultations conducted in Vanuatu following the monitoring workshops meant that the number of objectives and indicators used to support projects was reduced. As Leah Nimoho observed:

When I returned to Vanuatu with my draft monitoring plan, I originally had seven objectives to support our fisheries work in the IWP. However, after discussing the plan with stakeholders, we decided that this was too ambitious so we reduced the number of project objectives to three. Similarly, we considered that I may have selected too many indicators so we revised them and reduced the number. Rather than having 20 process indicators as I had in the draft, for example, I ended up with only seven specific ones that has some links to the stress reduction indicators and environmental status indicators. (Leah Nimoho, IWP Vanuatu, personal communication, 21 July 2005).

The IWP has since incorporated reporting on progress with monitoring to in-country quarterly narrative reports. NCs are required to outline monitoring activities undertaken and note how these relate to monitoring plans. In fact, partially because draft monitoring plans were only finalised in early 2005, only a few countries (Tonga, Niue, Fiji) have so far reported on monitoring. Box 1, for example, shows reporting on monitoring by Tonga in its March 2005 narrative report. It can be seen that the format closely followed the structure of the draft monitoring plan already noted in table 8.

##### 1	First quarterly narrative report for IWP Tonga: monitoring section

Monitoring

20. The status for process indicators.

(i) 	Process Indicator:

Nukuhetulu Project Working Group (NPWG) meets regularly and well attended.

Source of Verification:

Meeting minutes

Competition scorecard

Result of activities undertaken:

-	The NPWG met three times during the quarter and was well attended. In between these meetings, two general meetings with all the women in the village were held to discuss outstanding issues from 2004 activities. Issues discussed include the need for more participation and support from village people in project activities, and roaming pigs to be managed effectively.

The general meetings with women’s group conducted a participatory problem analysis. A tentative list of activities to address the problem was generated in response to the root causes of the problem. The meeting agreed that village competition is one of the most effective ways of involving people, and change from household/individual-based to block/group-based. The village is currently divided into five blocks and ranging from 10 – 15 households in each block.

-	Two leading members of each block were invited to participate in the NPWG meeting. The criteria and conditions of the competition were reviewed by the NPWG meeting and were passed on to the rest of the block through their respective leaders. Most of the blocks conducted their own weekly inspection prior to the project monthly inspection. The village clean up competition continued to focus on the following activities: household composting, home gardening, pig control, tree planting, proper disposal of non-biodegradable waste, tree planting and village cleanliness.

Upcoming activities:

-	The general meetings with women’s group also agreed to set up village regulations to control and reduce pigs negative impact on village environment. The issue was submitted and endorsed by the village fono in March and it is in the hands of the District Officer for further follow-up with the Crown Law Department.

-	The next competition judging will take place in April, May, and final in June. All the points will be tally-up and prizes will be awarded in June during the Environmental Awareness Week.

21. The status for environmental stress reduction indicators:

(i)	Environmental Stress Reduction Indicator:

more than 10 new households participating in composting and home gardening

Source of verification:

Photograph

Competition score card

Radio and TV program

Result of activities undertaken:

-	The judging of block/group-based competition started in March 2005 and will be awarded in June 2005. The first inspection in March recorded a total of 38 households composting in Nukuhetulu village. The 25 new composts were set up as a result of block/group inspection.

Upcoming activities:

-	Due to request from the new composters, the IWP and Tonga Trust is organising a follow-up meeting and on-site demonstration with all the new composters to further demonstrate setting up and proper maintenance of household compost.

-	The competition will continue to encourage setting up of new household composts as well as proper maintenance of the existing ones.

22. The status for environmental status indicators:

(i) 	 Environmental Status Indicators:

-	Improving the quality by reduction in quantity of nutrients presence in ground water and lagoon.

Source verification:

- 	water quality testing/monitoring report

Result of activities undertaken:

-	 sampling, data collection and part of the analysis is completed. Physical and biological data has been analysed while the pesticides analysis awaits results from NZ

Upcoming activities:

-	Upcoming activities the same water quality testing survey will be repeated in August and December 2005 and July 2006

Source: IWP Tonga (2005)

# 7	Conclusions

The IWP considers its work on the development of monitoring plans to be one of its most significant strategic activities to date. It could not have been achieved without the guidance of an experienced consultant. The PCU considers that all key players in the IWP – including the PCU – gained substantially from active involvement in the monitoring planning process.

In the experience of the IWP, the process used to develop the monitoring plans, and the templates provided, were extremely useful to countries in considering strategic monitoring plans (often for the first time). Feedback from NCs on the monitoring activities conducted was extremely positive. (See feedback question results at Annex 2). Particular strengths of the approach were:

- the development of objectives tables;

- the requirement to consider process, environmental stress reduction and environmental status indicators;

- the requirement to limit the overall number of indicators; and

- the focus on separate national versus local level activities (and the relationship between them).

This approach, adopted from the GEF, generally provided a useful approach to the development of indicators. It enabled project processes as well as outcomes to be monitored, and enabled the inclusion of indicators to assess long and short term impacts and outcomes. Ultimately, however, it must be noted that the changes addressed in stress reduction and environmental status indicators can be influenced by factors beyond project boundaries. It may in practice be difficult to isolate the influence of specific projects from influences of wider changes and developments in these areas.

Most importantly, the IWP approached the development of monitoring plans as a standard aspect of project planning. However, the activity turned out to be pivotal to focus in-country work. It provided a rationale for countries to revisit – or even explicitly consider for the first time – their implicit project aims and objectives. Clarifying project goals subsequently reaped benefits beyond those connected with monitoring. It took NCs through a strategic planning process which, for many of them, was the first time in their project. The process also brought to the fore the challenge that many NCs were facing with focusing and containing the scope of their projects. A focus on monitoring has thereby promoted a strategic approach to project planning in the IWP. Having said this, it required substantial time and resources to tease out and deal with monitoring issues. In relation to resources, this is especially important since few resources had initially been allocated to the stage of developing in-country monitoring plans (although resources had always been allocated for monitoring activities themselves). Further support may be needed in the future to help NCs interpret and document their monitoring findings.

Monitoring plans threw into perspective work that had been done to date. They highlighted where existing baseline work had been insufficient and identified tasks to fill baseline data gaps. In a sense, the draft monitoring plans became de facto work plans – or at least became a major part of them. Broad baseline data collection exercises were also found to provide valuable information for project planning.

Realistic monitoring plans need to be simple. IWP experience was that some countries got carried away with enthusiasm when developing monitoring plans. Instead, specifying a limit to the number of indicators to be used – and providing a list of criteria to select between competing indicators – will (and did in practice) help to keep the plans workable.

# References

Belfiore, S., (2003) 'The growth of integrated coastal management and the role of indicators in integrated coastal management: introduction to the special issue (Editorial)', Ocean and Coastal Management, 46:225-34.

Bowen, R.E. and Riley, C. (2003) 'Socio-economic indicators and integrated coastal management', Ocean and Coastal Management, 46:299-312.

Bunce, L. and Pomeroy, B. (2003) Socioeconomic Monitoring Guidelines for Coastal Managers in Southeast Asia (SocMon SEA), World Commission on Protected Areas and Australian Institute of Marine Science, Townsville.

Duda, A. (2002) Monitoring and Evaluation Indicators for GEF International Waters Projects, Monitoring and Evaluation Working Paper 10, November.

Earle, S., Carden, F. and Smutylo, T. (2001) Outcome Mapping: building learning and reflection into development programs, IDRC, Ottawa.

Guijt, I. and Abbot, J. (1998) Changing Views on Change: participatory approaches to monitoring the environment, IIED, London.

Hunnam, P. and Schuster, C. (2003) Mid-Term Evaluation Report: International Waters Project, Samoa, July.

IWP Tonga (2005) International Waters Programme Tonga Quarterly Update: Jan – Mar, 2005, Department of Environment, Tonga.

Lusthaus, C., Adrien, M. and Morgan, P. (2000) Integrating Capacity Development into Project Design and Evaluation, GEF, Washington DC.

Mahanty, S. (2004a) Report on the Monitoring Workshop of the Fourth National Coordinator’s Meeting 5-7 July 2004, SPREP, Apia.

Mahanty, S. (2004b) Developing Project Monitoring Plans Report on preparatory activities and the monitoring workshop of the Fifth National Coordinator’s Meeting, 25-29 October 2004, SPREP, Apia.

Mahanty, S., Holland, P., Stacey, N., Wright, A. and Menzies, S. Forthcoming, “Learning to learn: designing monitoring plans in the Pacific Islands International Waters Project”.

Margoluis, R. and Salafsky, N. (1998) Measures of Success: Designing Managing and Monitoring Conservation and Development Projects, Island Press, Washington DC.

Monitoring and Evaluation Unit (GEF) (2003) Program Performance Indicators for GEF International Waters Programs, GEF, Washington DC.

Nakashima, S. (1997) Integrated Coastal Management as Best Practice in GEF Project Development: Lessons Learned From Selected Biodiversity projects in Marine, Coastal and Freshwater Ecosystems, UNDP/GEF.

Olsen, S.B., 2003. 'Frameworks and indicators for assessing progress in integrated coastal management initiatives', Ocean and Coastal Management, 46:347-61.

Pasteur, K. (2001) Tools for Sustainable Livelihoods: livelihoods monitoring and evaluation: draft for comments, Institute of Development Studies, London.

Project Coordination Unit (2003) Guidelines for In-Country Arrangements: Selection of Focal Issues, Host Community and Project Strategic Planning and Design: Version 2.00 (pre-release), IWP, SPREP, March.

Russell, D. and Harshbarger, C. (2003) Groundwork for Community-Based Conservation: Strategies for Social Research, Altamira Press, Walnut Creek, CA.

Thorburn, R. (2003) The Identification of Indicators for Monitoring Stakeholder Participation in the International Waters Programme, unpublished paper for Masters of Applied Anthropology and Participatory Development, ANU, Canberra

United Nations Development Program and Global Environment Facility (1999) ‘Implementation of the Strategic Action Plan of the Pacific Small Island Developing States’, project document, Washington DC: GEF.

United Nations Development Program (2002) ‘Handbook on Monitoring and Evaluating for Results’, New York: UNDP Evaluation Office.

###### Annex 1	Terms of reference for the monitoring consultant

The Monitoring and Evaluation Specialist and Facilitator is engaged to:

- Provide support and advice to the PCU to review, and as appropriate, refine the IWP:

- log frame; and

- project monitoring and evaluation plan.

- Prepare any additional resource materials and subject matter to assist support discussions during NCM-4 to further refine the Project Log frame, the Project MEP and monitoring plans for community- and national level activities associated with addressing environmental concerns in relation to the IWP focal areas.

- In association with PCU staff, facilitate discussions during NCM-4 in relation to the Project Log frame, the Project MEP and monitoring plans for community- and national level activities in each IWP focal area.

- Provide a written report of the consultancy that clearly describes the work undertaken during the consultancy, details the outcomes achieved, and critically evaluates issues that could arise during implementation of the remainder of the Project in respect of i) the Log frame, ii) the Project MEP and iii) national level monitoring plans. A proposed schedule to keep project monitoring and evaluation activities under review for the remainder of the Project will be included in the report.

# Annex 2	Summary of Evaluation Responses

1. Level of satisfaction that the workshop has achieved its objectives?

Ranking->

- Level of satisfaction with the content of the workshop?

- Level of satisfaction with the training approach (learning by doing) and methods used?

- Level of satisfaction with the length (number of days) of the workshop.

- What has been the most useful or beneficial part of the training for you? Why?

- One on one assistance was excellent;

- The monitoring plan - it will get me prepared to start working

- Face to face interaction with PCU and Sango, Meg

- Discussing with each other

- Reframing of goals, objectives and activities

- Everything, because its assist in linking our work with others

- Individual monitoring and evaluation plans

- ESRI - the end product of success and failure of the project

- Having someone (expert) talk and work with my plan

- Everything - gives more understanding of monitoring plans

- What parts of the training should be strengthened or expanded in the future?

- Approach was satisfactory

- Its perfect, maybe if I get started working I'll give you some inputs in the future

- Be more clear on format

- Case studies like the ones in Samoa NCM-4

- Lateral thinking

- Linking goals, objectives and activities

- Identifying good indicators

- More time

- Very much effective

- What's next after monitoring plan done

- Indicators and maybe Goals and Objectives identification

- What changes have you experienced in your knowledge, skills and attitudes as a result of the training?

- Improved in all aspects

- Many, such as making a monitoring plan, meeting with the IWP staff

- Not much!  But I like the fact the M&E plan has provided clearer direction for my project

- More focused on issues

- Focusing of plan

- Merging and selecting the appropriate indicators

- Managed to think very strategic

- Knowledge and skill improved from NCM4

- Need more following up now and address the challenges

- More focused, clear where I'm heading and activities in between

- Being able to see a clear way forward for the program in terms of how to deal with the problems

- What follow-up support or advice do you think you might need over the coming months in facilitating participatory planning (monitoring) activities with stakeholders?

- Email contact would be helpful in case problems are encountered

- More training and advice from PCU and experts dealing with RMI focal points

- Entry of new data into M&E

- Explaining M&E plan with key stakeholders and govt.

- Need to keep contact with Sango and PCU alive

- Keep in contact

- Need some email support from Sango M.

- Time and commitment of the community and key stakeholders

- Not sure now but I'm sure there will be

- All

- Other suggestions or comments?

- Would it be possible to compile a manual on compiling M&E plans?  A simplified instruction booklet..

- Yeah, more training.

- Its great, but I would prefer if more time could have been spent on the definition of M&E terminology with easy examples

- Thank you very much for your time and effort - it have been great work, excellent

- None, just thank for your time and effort.  Job well done.

- Implementation of the plans to have a mentor apart from PCU

- Very interesting, many thanks

- Keeping in touch

# Footnotes

International Waters is one of four focal areas of Global Environment Facility (GEF) supported activities. International Waters, as defined by the GEF, include oceans, large marine ecosystems, enclosed or semi-enclosed seas and estuaries as well as rivers, lakes, groundwater systems, and wetlands with trans-boundary drainage basins or common borders involving two or more countries. The ecosystems and habitats associated with these waters are essential parts of the system.

These were identified during the formulation of the Strategic Action Programme for the International Waters of the Pacific Small Island Developing States (SAP). The SAP provided the basis for Project design (see SPREP 1998).

This approach is based on lessons learned and best practice from the region and elsewhere. In relation to lessons learned from previous GEF projects, Nakashima (1997:16) described the need to use a ‘two-tracked approach’ to resource management to build capacity at the national level for policy regulation while integrating implementation activities at the local or community level.

The IWP was fortunate to have the expertise of a consultant with previous experience in both natural resource management and Pacific conservation efforts generally, and experience in supporting the IWP specifically.

# Text boxes

Number of respondents

Number of respondents

Ranking

Number of respondents

Lessons

adaptation

implementation

Pilot project

Strategic planning and design

Monitoring

Focal issue identified and host community selected

Evaluation

Ranking

Number of respondents

Ranking